## Sheet1
	E-commerce Charter
Project Name :		MSC Class Website

Project Manager:		Kamlesh Kshirsagar			Contact :		kamleshkshirsagar@gmail.com

Status:		Approved

Start and End Date:		Start Date: 23/01/2025 End Date: 30/06/2025
		Start: Jan 24 End: Sept25
Project Description:		The project is to design the E-Commerce website for the company for selling the products of any company on an online website portal.Customers can record their purchases.

Project Team:		1.Kamlesh Kshirsagar					Project Manager

		2. Nikhil Nagawade					Team Lead

		3. Omkar Mule					Team Member

		4. Satish Bhor					Team Member

		5. Abhishek Magar					Team Member

Project scope:		The E-com website allow us to buy any product of any category based on customer choices.It allow user to store or add the product into the wishlist or cart.

Constrains:		Time:		6 months
		Budget:		20 lakh
		Quality:		Prioritize time & budget

Benefits		Helps to ensure the project is in implementation as per decided.
		Helps to build the product which handles many customers at a time without any problem.
		Ensure the product deployment has to be done within decided time.
Project Objective:		Develop a user-friendly and visually appealing website for a specific class. / Provide students and teachers with a centralized online platform for accessing course materials, announcements, grades, and communication. / Enhance student engagement and facilitate effective learning. / Improve communication and collaboration between students and teachers.

Key Stakeholders:		Project Manager
		Project Team
		Owner
		Students
Timeline And Key Milestone:		23 Jan : 31 Jan: Estimate the Website Cost
		2 Feb : 20 Feb Estimate time and resources
		20 Feb : 10 March Design the user interface
		10 March : 29 March building the database
		29 March : 3 may start building the website
		4 May : 20 May Test the website and measure performance
		3 June April launch the website
		30 June Closing
Risks:		Budget goes beyond the decided amount. More time is Required than Decided. Developer may do not have any previous experience regarding real time project.

Comments (If Any):